## Sheet1
Credit Card
Estimation Sheet on Change Requirements
Creation Date: <12 July 2021
SPECIFICATION | Size | Complexity | Best | Worst | Likely | Estimated
Module-1
Prepare insert script and insert into DB for type,user,role,state transaction |  |  | 8 | 12 | 10 | 10
service class, model class, sp, table, tr for T_CREDIT_CARD table |  |  | 4 | 6 | 5 | 5
add column and update service class, model class, sp, table, tr for T_CUSTOMER table |  |  | 4 | 6 | 5 | 5
add column and update service class, model class, sp, table, tr for T_EXISTING_LIABILITY table |  |  | 4 | 6 | 5 | 5
service class, model class, sp, table, tr for T_DOCUMENT table |  |  | 4 | 6 | 5 | 5
service class, model class, sp, table, tr for T_CARD_CONFIG table |  |  | 4 | 6 | 5 | 5
service class, model class, sp, table, tr for T_CARD_DOC_MAP table |  |  | 4 | 6 | 5 | 5 | 40
Credit Card type configuration option in admin panel |  |  | 6 | 10 | 8 | 8
Customer type configuration in admin panel to for cc |  |  | 6 | 10 | 8 | 8
Interest rate configuration on admin panel depending on customer type and card type |  |  | 4 | 6 | 5 | 5
Document list configuration on GUI depending on customer type and card type |  |  | 8 | 10 | 9 | 9
Create new Credit Card icon for open CC panel pop-up |  |  | 2 | 4 | 3 | 3
Search panel for credit card |  |  | 12 | 15 | 14 | 13.8333
Search result show grid |  |  | 8 | 12 | 10 | 10
New CC Module create option int tree && create new tree for cc panel left corner |  |  | 8 | 12 | 10 | 10
CC Details design in UI show |  |  | 20 | 28 | 24 | 24
CC Save , Update , other |  |  | 20 | 28 | 24 | 24
Create Customer search panel in cc details for |  |  | 8 | 12 | 10 | 10
Action performance and action permission in CC |  |  | 12 | 16 | 14 | 14
Documents upload && view |  |  | 8 | 8 | 8 | 8
Existing liabilities, Limit & DBR Analysis calculate |  |  | 8 | 8 | 8 | 8
Card Limit & EMI Capture and save/update |  |  | 9 | 9 | 9 | 9
Role and permission based Field Hide/show |  |  | 8 | 8 | 8 | 8
Card Type based field hide/show |  |  | 15 | 15 | 15 | 15
Allowing to do query |  |  | 20 | 28 | 24 | 24
Dynamically showing Signatories and staff ID |  |  | 8 | 8 | 8 | 8
<Age limit validation on remitter information creation> | L | High | 2 | 3 | 2 | 2.1667
KYC, CIB checking & Validation |  |  | 5 | 5 | 5 | 5
Department wise state /workflow management |  |  | 6 | 6 | 6 | 6
Application grouping and Memo Generate |  |  | 20 | 24 | 22 | 22
Generating report |  |  | 60 | 80 | 70 | 70
Show work history |  |  | 40 | 48 | 40 | 41.3333
TOTAL HOURS/MAN | [5 empty] | 405.3333
ESTIMATED TIMELINE | 8
WORKING HOUR PER DAY
ESTIMATED DAYS/MAN = ESTIMATED HOURS/WORKING HOURS PER DAY | 3
NUMBER OF DEVELOPERS IN THE TEAM (VOLUME)
HOLIDAYS + LEAVE DAYS TOTAL IN THE TEAM
TOTAL REQUIRED DAYS/MAN = ESTIMATED DAYS + HOLIDAYS + LEAVE DAYS
TOTAL REQUIRED DAYS/TEAM = TOTAL REQUIRED DAYS/TEAM VOLUME
QUALITY ASSURANCE (DAYS/TEAM)
BUFFER (DAYS/TEAM)
ESTIMATED DAYS/TEAM = ESTIMATED DAYS + QUALITY ASSURANCE + BUFFER
DELIVERY DATE AS PER CALENDAR :